## Project Charter
Project Charter Document
GENERAL PROJECT INFORMATION |  |  |  | DEFINE THE PROJECT RESOURCES AND COSTS
PROJECT NAME | E-commerce Platform for Small Businesses | EMAIL ADDRESS | ecommerce@businesshub.com | PROJECT TEAM | Developers, Testers, Project Manager, UI/UX Designers,
PROJECT SPONSOR | Businesshub Inc. | PHONE NUMBER | 854-566-8615 | SUPPORT RESOURCES | MS Project, AWS, JIRA, APPIUM, Whiteboards, Office 365, PCs, Internet Connection, Wireframe tools, Freelancers
PROJECT MANAGER | John Doe | EXPECTED START DATE | 2020-04-23 | SPECIAL NEEDS | N/A
ESTIMATED COSTS | 5290 | EXPECTED COMPLETION DATE | 2020-05-25
|  |  |  | COST TYPE | VENDOR / LABOR NAMES | RATE($) | QTY / HR | AMOUNT
DESCRIBE THE PROBLEM OR ISSUE, GOALS, OBJECTIVES, AND DELIVERABLES OF THIS PROJECT |  |  |  | Cloud Services | AWS | 150 | 8 | 1200
PROBLEM OR ISSUE | Have to visit web application every time something needs to be changed, Trouble managing inventory, Consistency of data even after making changes on slow internet connection, Complex and Time consuming |  |  | Freelancer A | Mr A | 2000 | 1 | 2000
PURPOSE OF PROJECT | Provide solution by building an application for the ease of access imitating the web application |  |  | Freelancer B | Mr B | 2000 | 1 | 2000
BUSINESS CASE | To increase the revenue, to add one more project in the portfolio and showcase the work. |  |  | MISCELLANEOUS | Stationary items | 10 | 9 | 90
GOALS / METRICS | Becoming an expert by doing similar projects and increase the revenue by 5% by June 1, 2020 |  |  | TOTAL COSTS |  |  |  | 5290
EXPECTED DELIVERABLES | An android application that is synchronised with a web application but with more services and flexibility
DEFINE THE PROJECT BENEFITS AND CUSTOMERS
DEFINE THE PROJECT SCOPE AND SCHEDULE |  |  |  | PROCESS OWNER | John Doe
WITHIN SCOPE | Inventory management, activities management, blog management, registered business' details, data accessibility, goods categorization, provide work hours, support 3 languages: French, English, Dutch |  |  | KEY STAKEHOLDERS | Management body, Developers, Designers, Managers, Users, Customer's customers, Sales & Marketing team, Freelancers
OUTSIDE OF SCOPE | Support other than required 3 languages, Adding more services to web application, Adding more services to mobile application other than requirements, security measures, 2-factor authentication or biometrics for login, Sharing audios/videos |  |  | FINAL CUSTOMER | Nearshop
SCHEDULE | KEY MILESTONE | START | FINISH | EXPECTED BENEFITS | Small businesses can be found on one platform with all the details
| Project Charter | 2020-04-23 | 2020-04-27
| Project Scope with WBS | 2020-04-28 | 2020-04-29 | DESCRIBE PROJECT RISKS, CONSTRAINTS, AND ASSUMPTIONS
| Requirement Gathering & Analysis | 2020-04-30 | 2020-05-01 | RISKS | Fulfilling the challenge of synchronization with backend, Application working with all 3 languages, Providing flexibility to user satisfaction
| Design | 2020-05-04 | 2020-05-06 | CONSTRAINTS | Application must include all the services which are available on web application, Any type of businesses should be registered, App should display data in any of 3 languages, App should be user-friendly in terms of ease of operation and flexibility
| Development | 2020-05-06 | 2020-05-15 | ASSUMPTIONS | Application can be used by anyone even for whom who are not experts of using mobile, Customers will be able to manage their business easily
| Testing | 2020-05-13 | 2020-05-18
| Deployment | 2020-05-19 | 2020-05-20 | Prepared by: | Trisha Solanki | Date: | 2020-04-22
| Post Implementation Review | 2020-05-21 | 2020-05-25

## Stakeholders
Stakeholders
Internal | External | External Indirectly | Relationship
Businesshub Inc. | Nearshop (Client) | Marketing & Sales Team | Money
Senior Management Team | Freelancers | Suppliers | Communication
Project Manager | Customers | Buyers | Product Development
Developers | Sponsors | Employees of small businesses | Shopping
Designers | Investors | Competitors | Supply
Testers |  |  | Use Application
Investment
Sponsorship
Salary
Marketing
Competition

## Project Deliverables
Project Deliverables List
Tasks | Sub-tasks
Project Initiation and Planning | Project Charter Document
Stakeholders List
Project Deliverables
WBS
Gantt Chart and Network Diagram
Project Communication Plan
Analysis | Requirements List
Business Requirements
Business Requirements to Functional Requirements
Risks and Responses
5 types of conflicts and how to resolve them
Design | Wireframes
Flowcharts, Use case diagram, and Sequence diagram
Application Architecture and Technical Design
Technical Design Document
Development | Application Implementation Plan
Front-end source code
Back-end source code
Report of Data Conversion and Synchronization
Testing | Detailed Test Plan
Test Scenarios, Test Cases, and Test Scripts
Test Results Documentation
Deployment | Readiness Evaluations Reports
Application Defect Resolution Reports
Application Source Code and Documentation
Documented Implementation Project Closeout

## Conflicts & Resolution
Conflicts and Resolution
Conflicts Types | Conflicts Examples | Style | Resolution Type | Resolution | Conflict Resolutions Measure
Group Differences / Conflicts arisen from Cultural differences | As different cultures speak different languages, the people from outside of your community feel left aside and work will not be able to as smoothly as PM wants | Accommodation | Smoothing | Introduce each other well and organize activities to mix the different people from different cultures | Resolution Type | Common result | Style | Purpose | Effect
Project Vision / Conflicts arisen from Project priorities | It happens when different stakeholders have different expectations. At some point of time you won't be able to fulfil everyone's wish if you won't maintain balance | Win-win, Collaboration | Problem solving or confrontation | Try to keep everyone happy! If that is not possible then come up with a mid-way solution that everyone can agree upon | Forcing | win-lose | Avoidance | I don’t want to deal with the conflict. | “You win.”
Conflict Disagreements / Conflicts arisen from individual personalities | Different team members have different personalities, some members are authoritative and some are shy. It can easily lead to unproductive performance of the whole team | Competition, Compromise | Withdrawing, Compromising | Try to assign tasks according to the personalities of team members so that some members can not enjoy and others does not have to suffer | Smoothing | yield-lose | Accommodation | I’ll let you have your way and it’s O.K. | “You win.”
Poor Leadership / Conflicts arisen from the Team environment | Project can be completed by people and resources. If resources are not allotted properly to all team members then it is likely that the whole project can go south | Compromise | Compromising | Make a matrix which can be allotment timetable for resources so that resources can be utilized and no one has to wait | Withdrawing | lose-leave | Competition | I’m going to get what I want and you’re not. | “I win, you lose.”
Lack of Communication | Giving wrong or unclear instructions can set a project back. A project manager that fails to communicate in a clear way will set up the project for failure. | Avoidance | Forcing | Communicating with your team members is crucial. So PM should communicate as much as possible. That keeps the whole team together and up & running in the same direction | Compromising | moderate lose-moderate lose | Compromise | I’ll give a little and you give a little. | “We both win a little and lose a little.”
[5 empty] | Problem solving or confrontation | integrative | Win/Win or Collaboration | We both get what we need when we listen to each other and work together. | “We both win the most.”

## Communication Plan
Communication Plan
Communication | Frequency | Goal | Owner | Audience
Synchronous Communication
Meetings
Team meeting | Daily | Discuss what each team member did yesterday, what they'll do today, and any blockers | Project manager | Project team
Project review | At milestones | Present project deliverables, gather feedback, and discuss next steps | Project manager | Project team + Project sponsor
Post-mortem meeting | At end of project | Assess what worked and what did not work and discuss actionable takeaways | Project manager | Project team
Team stand-up
Task progress updates | Daily | Share daily progress made on project tasks | Project manager | Project team
Video Conference Calls
Major work updates | Weekly | Share weekly progress made on project tasks and give major updates on project | Project manager | Project team + Client + Senior Management
Asynchronous Communication
Email
Project status report | Weekly | Review project status and discuss potential issues or delays | Project manager | Project team + Project sponsor + Senior Manager

## WBS
Work Breakdown Structure (WBS)
WBS Code | Task Name | Duration | Start | Finish | Predecessors
E1 | E-commerce Platform for Small Businesses | 73 days | Wed 06-05-20 | Fri 14-08-20
E1/1 | Project Initiation and Planning | 13 days | Wed 06-05-20 | Fri 22-05-20
E1/1.1 | Define Project Charter | 2 days | Wed 06-05-20 | Thu 07-05-20
E1/1.2 | Identify Stakeholders | 2 days | Fri 08-05-20 | Mon 11-05-20 | 3
E1/1.3 | Create Project Deliverables | 5 days | Fri 08-05-20 | Thu 14-05-20 | 3
E1/1.4 | Create Scope Statement including WBS | 3 days | Fri 15-05-20 | Tue 19-05-20 | 5
E1/1.5 | Create Project Schedule and Timeline (Gantt Chart and network diagram) | 3 days | Wed 20-05-20 | Fri 22-05-20 | 6
E1/1.6 | Create Project Communication Plan | 2 days | Tue 12-05-20 | Wed 13-05-20 | 4
E1/2 | Analysis | 9 days | Wed 20-05-20 | Mon 01-06-20
E1/2.1 | Requirement Gathering and Analysis | 4 days | Wed 20-05-20 | Mon 25-05-20 | 6
E1/2.2 | Gather Business Requirements | 3 days | Tue 26-05-20 | Thu 28-05-20 | 10
E1/2.3 | Convert Business Requirements to Functional Requirements | 2 days | Fri 29-05-20 | Mon 01-06-20 | 11
E1/2.4 | Identify 5 types of conflicts and how to resolve them | 2 days | Tue 26-05-20 | Wed 27-05-20 | 6,10
E1/2.5 | Identify Risks and Responses | 2 days | Thu 28-05-20 | Fri 29-05-20 | 13
E1/3 | Design | 9 days | Tue 02-06-20 | Fri 12-06-20
E1/3.1 | Create wire-frames | 4 days | Tue 02-06-20 | Fri 05-06-20 | 12
E1/3.2 | Prepare Flowcharts, Use case diagram, and Sequence diagram | 2 days | Tue 02-06-20 | Wed 03-06-20 | 12
E1/3.3 | Application Architecture and Technical Design | 3 days | Mon 08-06-20 | Wed 10-06-20 | 16
E1/3.4 | Create Technical Design Document | 2 days | Thu 11-06-20 | Fri 12-06-20 | 18
E1/4 | Development | 27 days | Mon 15-06-20 | Tue 21-07-20
E1/4.1 | Application Implementation Plan | 4 days | Mon 15-06-20 | Thu 18-06-20 | 19
E1/4.2 | Front-end development | 10 days | Fri 19-06-20 | Thu 02-07-20 | 21
E1/4.3 | Back-end development | 10 days | Fri 19-06-20 | Thu 02-07-20 | 21
E1/4.4 | Data Conversion, Synchronization, and Reporting | 5 days | Fri 03-07-20 | Thu 09-07-20 | 22,23
E1/4.5 | Application Maintenance, Support and Transition | 8 days | Fri 10-07-20 | Tue 21-07-20 | 24
E1/5 | Testing | 31 days | Fri 19-06-20 | Fri 31-07-20
E1/5.1 | Detailed Test Plans | 2 days | Fri 19-06-20 | Mon 22-06-20 | 21
E1/5.2 | Create Test Scenarios, Test Cases, and Test Scripts | 4 days | Tue 23-06-20 | Fri 26-06-20 | 27
E1/5.3 | Document Test Results | 5 days | Wed 22-07-20 | Tue 28-07-20 | 25,28
E1/5.4 | Error handling & Improvements | 3 days | Wed 29-07-20 | Fri 31-07-20 | 29
E1/6 | Deployment | 18 days | Wed 22-07-20 | Fri 14-08-20
E1/6.1 | Release Readiness Evaluations and Reports | 3 days | Mon 03-08-20 | Wed 05-08-20 | 30
E1/6.2 | Application Defect Resolution Reports | 2 days | Thu 06-08-20 | Fri 07-08-20 | 30,32
E1/6.3 | Application Source Code and Documentation | 4 days | Wed 22-07-20 | Mon 27-07-20 | 20
E1/6.4 | Documented Implementation Project Closeout | 5 days | Mon 10-08-20 | Fri 14-08-20 | 34,26,33

## Cost
Cost Management
Task Name | Cost | Fixed_Cost | Total_Cost | Baseline_Cost | Cost_Variance | Actual_Cost | Remaining_Cost | RESOURCE COST VARIANCE | COST STATUS
E-commerce Platform for Small Businesses | $5,290.00 | 0 | 5290 | 0 | 5290 | 26 | 5264
Project Initiation and Planning | $30.00 | 0 | 30 | 0 | 30 | 26 | 4
Define Project Charter | $10.00 | 0 | 10 | 0 | 10 | 10 | 0
Identify Stakeholders | $10.00 | 0 | 10 | 0 | 10 | 10 | 0
Create Project Deliverables | $10.00 | 0 | 10 | 0 | 10 | 6 | 4
Create Scope Statement including WBS | $0.00 | 0 | 0 | 0 | 0 | 0 | 0
Create Project Schedule and Timeline (Gantt Chart and network diagram) | $0.00 | 0 | 0 | 0 | 0 | 0 | 0
Create Project Communication Plan | $0.00 | 0 | 0 | 0 | 0 | 0 | 0
Project Planning done | $0.00 | 0 | 0 | 0 | 0 | 0 | 0
Analysis | $20.00 | 0 | 20 | 0 | 20 | 0 | 20
Requirement Gathering and Analysis | $0.00 | 0 | 0 | 0 | 0 | 0 | 0
Gather Business Requirements | $0.00 | 0 | 0 | 0 | 0 | 0 | 0
Convert Business Requirements to Functional Requirements | $0.00 | 0 | 0 | 0 | 0 | 0 | 0
Identify conflicts and how to resolve them | $10.00 | 0 | 10 | 0 | 10 | 0 | 10
Identify Risks and Responses | $10.00 | 0 | 10 | 0 | 10 | 0 | 10
Analysis completed | $0.00 | 0 | 0 | 0 | 0 | 0 | 0
Design | $10.00 | 0 | 10 | 0 | 10 | 0 | 10
Create wireframes | $0.00 | 0 | 0 | 0 | 0 | 0 | 0
Prepare Flowcharts, Use case diagram, and Sequence diagram | $10.00 | 0 | 10 | 0 | 10 | 0 | 10 | COST DISTRIBUTION
Application Architecture and Technical Design | $0.00 | 0 | 0 | 0 | 0 | 0 | 0
Create Technical Design Document | $0.00 | 0 | 0 | 0 | 0 | 0 | 0
Design phase finished | $0.00 | 0 | 0 | 0 | 0 | 0 | 0
Development | $4,600.00 | 0 | 4600 | 0 | 4600 | 0 | 4600
Application Implementation Plan | $0.00 | 0 | 0 | 0 | 0 | 0 | 0
Front-end development | $2,150.00 | 0 | 2150 | 0 | 2150 | 0 | 2150
Back-end development | $2,150.00 | 0 | 2150 | 0 | 2150 | 0 | 2150
Data Conversion, Synchronization, and Reporting | $150.00 | 0 | 150 | 0 | 150 | 0 | 150
Application Maintenance, Support and Transition | $150.00 | 0 | 150 | 0 | 150 | 0 | 150
Development and Implementation done | $0.00 | 0 | 0 | 0 | 0 | 0 | 0
Testing | $320.00 | 0 | 320 | 0 | 320 | 0 | 320
Detailed Test Plans | $10.00 | 0 | 10 | 0 | 10 | 0 | 10
Create Test Scenarios, Test Cases, and Test Scripts | $10.00 | 0 | 10 | 0 | 10 | 0 | 10
Document Test Results | $150.00 | 0 | 150 | 0 | 150 | 0 | 150
Error handling & Improvements | $150.00 | 0 | 150 | 0 | 150 | 0 | 150
Application Testing done | $0.00 | 0 | 0 | 0 | 0 | 0 | 0
Deployment | $310.00 | 0 | 310 | 0 | 310 | 0 | 310
Release Readiness Evaluations and Reports | $0.00 | 0 | 0 | 0 | 0 | 0 | 0
Application Defect Resolution Reports | $150.00 | 0 | 150 | 0 | 150 | 0 | 150
Application Source Code and Documentation | $150.00 | 0 | 150 | 0 | 150 | 0 | 150
Documented Implementation Project Closeout | $10.00 | 0 | 10 | 0 | 10 | 0 | 10
Project Finished | $0.00 | 0 | 0 | 0 | 0 | 0 | 0

## Risk & Responses
Risk and Responses
Risk ID | Asset | Description | Severity | Likelihood | Level | Mitigations / Warnings / Response | Measures
R01 | Internal | What if the database will crash under the situation of multiple access? | Intolerable | Possible | High | Keep the database on cloud services so that the whole database can be retrieved in such cases | Asset | Risk Severity | Risk Likelihood | Risk Level
R02 | Internal | What if the application won't be finished on time? | Tolerable | Possible | Low | Use fast-tracking technique to avoid such kind situation | External | Acceptable | Improbable | Low
R03 | External | What if the customer brings new ideas and requirements once the development has started? | Acceptable | Probable | Low | You should always be ready to make the changes in application. Warn Designers and Developers about it beforehand | Internal | Tolerable | Possible | Medium
R04 | External | What if the freelancer(s) leave the work in the middle of the project under some circumstances? | Undesirable | Probable | High | Keep the list of Freelancers in case if you need to hire new ones |  | Undesirable | Probable | High
R05 | External | What if the customer is not satisfied with the final product? | Acceptable | Possible | High | Ask for feedback and make changes accordingly |  | Intolerable |  | Extreme
R06 | Internal | What if all the requirements won't be implemented by developers? | Intolerable | Possible | Extreme | Find an expertise or someone more experienced in this field and be ready to get help in times like this
R07 | Internal/External | What if project sponsor cuts the funding and/or resources? | Undesirable | Possible | High | Put some money from the allotted amount aside from the beginning in case of the sponsor stops funding/resources
R08 | Internal | What if the server crashes? | Intolerable | Possible | Extreme | Be ready to take action and keep the developers at phone call's reach to solve the issue as soon as possible
R09 | External | What if any external tool/software used in the project malfunctions? | Tolerable | Improbable | Medium | Make sure you have the alternate tools/software to use in case of failure
R10 | External | What if the final product is not user friendly as expected to the customer and users? | Undesirable | Probable | Low | In testing phase, test this application within a large number of users to avoid such conditions