## Task_Costs
ID | Active | Task_Mode | Task_Name | Fixed_Cost | Total_Cost | Baseline_Cost | Cost_Variance | Actual_Cost | Remaining_Cost
1 | Yes | Auto Scheduled | E-commerce Platform for Small Businesses | 0 | 5290 | 0 | 5290 | 26 | 5264
2 | Yes | Auto Scheduled | Project Initiation and Planning | 0 | 30 | 0 | 30 | 26 | 4
3 | Yes | Auto Scheduled | Define Project Charter | 0 | 10 | 0 | 10 | 10 | 0
4 | Yes | Auto Scheduled | Identify Stakeholders | 0 | 10 | 0 | 10 | 10 | 0
5 | Yes | Auto Scheduled | Create Project Deliverables | 0 | 10 | 0 | 10 | 6 | 4
6 | Yes | Auto Scheduled | Create Scope Statement including WBS | 0 | 0 | 0 | 0 | 0 | 0
7 | Yes | Auto Scheduled | Create Project Schedule and Timeline (Gannt Chartand network diagram) | 0 | 0 | 0 | 0 | 0 | 0
8 | Yes | Auto Scheduled | Create Project Communication Plan | 0 | 0 | 0 | 0 | 0 | 0
9 | Yes | Auto Scheduled | Project Planning done | 0 | 0 | 0 | 0 | 0 | 0
10 | Yes | Auto Scheduled | Analysis | 0 | 20 | 0 | 20 | 0 | 20
11 | Yes | Auto Scheduled | Requirement Gathering and Analysis | 0 | 0 | 0 | 0 | 0 | 0
12 | Yes | Auto Scheduled | Gather Business Requirements | 0 | 0 | 0 | 0 | 0 | 0
13 | Yes | Auto Scheduled | Convert Business Requirements to Functional Requirements | 0 | 0 | 0 | 0 | 0 | 0
14 | Yes | Auto Scheduled | Identify conflicts and how to resolve them | 0 | 10 | 0 | 10 | 0 | 10
15 | Yes | Auto Scheduled | Identify Risks and Responses | 0 | 10 | 0 | 10 | 0 | 10
16 | Yes | Auto Scheduled | Analysis completed | 0 | 0 | 0 | 0 | 0 | 0
17 | Yes | Auto Scheduled | Design | 0 | 10 | 0 | 10 | 0 | 10
18 | Yes | Auto Scheduled | Create wireframes | 0 | 0 | 0 | 0 | 0 | 0
19 | Yes | Auto Scheduled | Prepare Flowcharts, Use case diagram, and Squence diagram | 0 | 10 | 0 | 10 | 0 | 10
20 | Yes | Auto Scheduled | Application Architecture and Technical Design | 0 | 0 | 0 | 0 | 0 | 0
21 | Yes | Auto Scheduled | Create Technical Design Document | 0 | 0 | 0 | 0 | 0 | 0
22 | Yes | Auto Scheduled | Design phase finished | 0 | 0 | 0 | 0 | 0 | 0
23 | Yes | Auto Scheduled | Development | 0 | 4600 | 0 | 4600 | 0 | 4600
24 | Yes | Auto Scheduled | Application Implementation Plan | 0 | 0 | 0 | 0 | 0 | 0
25 | Yes | Auto Scheduled | Front-end development | 0 | 2150 | 0 | 2150 | 0 | 2150
26 | Yes | Auto Scheduled | Back-end development | 0 | 2150 | 0 | 2150 | 0 | 2150
27 | Yes | Auto Scheduled | Data Conversion, Synchronization, and Reporting | 0 | 150 | 0 | 150 | 0 | 150
28 | Yes | Auto Scheduled | Application Maintenance, Support and Transition | 0 | 150 | 0 | 150 | 0 | 150
29 | Yes | Auto Scheduled | Development and Implementation done | 0 | 0 | 0 | 0 | 0 | 0
30 | Yes | Auto Scheduled | Testing | 0 | 320 | 0 | 320 | 0 | 320
31 | Yes | Auto Scheduled | Detailed Test Plans | 0 | 10 | 0 | 10 | 0 | 10
32 | Yes | Auto Scheduled | Create Test Scenarios, Test Cases, and Test Scripts | 0 | 10 | 0 | 10 | 0 | 10
33 | Yes | Auto Scheduled | Document Test Results | 0 | 150 | 0 | 150 | 0 | 150
34 | Yes | Auto Scheduled | Error handling & Improvements | 0 | 150 | 0 | 150 | 0 | 150
35 | Yes | Auto Scheduled | Application Testing done | 0 | 0 | 0 | 0 | 0 | 0
36 | Yes | Auto Scheduled | Deployment | 0 | 310 | 0 | 310 | 0 | 310
37 | Yes | Auto Scheduled | Release Readiness Evaluations and Reports | 0 | 0 | 0 | 0 | 0 | 0
38 | Yes | Auto Scheduled | Application Defect Resolution Reports | 0 | 150 | 0 | 150 | 0 | 150
39 | Yes | Auto Scheduled | Application Source Code and Documentation | 0 | 150 | 0 | 150 | 0 | 150
40 | Yes | Auto Scheduled | Documented Implementation Project Closeout | 0 | 10 | 0 | 10 | 0 | 10
41 | Yes | Auto Scheduled | Project Finished | 0 | 0 | 0 | 0 | 0 | 0